## Implementation Plan Guidance
TALENT MANAGEMENT IMPLEMENTATION PLAN - GUIDANCE ON COMPLETION
Creating your Implementation Plan
It is recommended that you read the accompanying talent management implementation guidance. These templates can be used to illustrate the key deliverables that your organisation has identified in relation to talent mangement, the time period over which you expect to embed various interventions, the lead in this area and any observations/comments it is relevant for other key stakeholders to take into consideration. Your plan should be derived from your strategy and provide more detail as to what will be delivered, by whom and by when. You may also wish to capture the status of the deliverable (e.g. achieved, underway, not started) and/or any risk and mitigating actions that you have identified.
Your Implementation Plan will be dependent on a number of factors including:
· The stage you are at (e.g. just getting started, underway, wider roll-out, evaluating your approach)
· The size of your organisation
· The resources you have available to support implementation
· Other organisational factors including involvement in change/transformation, stability of leadership, effectiveness of engagement of and communication stakeholders etc.
It is suggested that you complete your plan once your organisational strategy and priorities have been defined, and that you review your plans regularly to monitor progress and update and/or change as necessary. Your deliverables may also be informed by suggested areas for action that have been identified through completion of the Talent Management Diagnostic Tool.
Example Plans
The next tabs provide examples of implementation plans containing a number of key deliverables an organisation may wish to focus on - these are interchangeable with you own areas of priority and a blank template has also been provided for your use.

## EXAMPLE A
EXAMPLE TM Implementation Plan | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | STATUS | ACTION OWNER | Comments on progress/additional resources needed/update on risks/actions:
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Developing your definition and strategy
Create a clear definition of talent management for the organiation | bar: Q1 Apr to Q1 Jun
Develop a clear strategy for talent management | bar: Q1 Apr to Q1 Jun
Outline talent management approaches for staff at all levels | bar: Q1 Apr to Q1 Jun
Align talent strategy to wider organisational and system priorities | bar: Q1 Apr to Q1 Jun
Establish clear priorities and objectives to achieve through talent management | bar: Q1 Apr to Q1 Jun
Planning for implementation
Identify the tools and processes that will be used for staff at all levels | bar: Q1 Apr to Q1 Jun
Identify a wide range of development opportunities for staff at all levels | bar: Q1 Apr to Q1 Jun
Ensure talent management is connected to other people and OD interventions | bar: Q1 Apr to Q1 Jun
Establishing Board/Governing Body accountability
Ensure talent management is recognised as a strategic priority | bar: Q1 Apr to Q1 Jun
Assign responsibility to named Board/Governing Body member | bar: Q1 Apr to Q1 Jun
Ensure talent management is a standing item on Board agendas | bar: Q1 Apr to Q1 Jun
Engaging the wider workforce
Establish roles and responsibilities for talent management and reflect | bar: Q2 Jul to Q2 Sep
Communicate talent management principles and approaches at all levels | bar: Q2 Jul to Q2 Sep
Reflect talent management responsibilities in the values and behaviours | bar: Q2 Jul to Q2 Sep
Reflect talent management responsibilities in job descriptions | bar: Q2 Jul to Q2 Sep
Ensure line managers and leaders are skilled in hosting talent conversations | bar: Q2 Jul to Q2 Sep
Brief staff in their role in preparing for talent conversations | bar: Q2 Jul to Q2 Sep
Information systems and reporting
Implement a system to capture performance, potential, aspirations, readiness and development | bar: Q2 Jul to Q2 Sep
Identify opportunities to link information about talent to organisational KPIs | bar: Q2 Jul to Q2 Sep
Establish reporting infrastructure at team/service and divisional levels | bar: Q2 Jul to Q2 Sep
Establish guideance for the management and use of talent data | bar: Q2 Jul to Q2 Sep
Equality, Diversity and Inclusion in Talent Management
Consider the Equality, Diversity and Inclusion implications of talent management approaches | bar: Q1 Apr to Q1 Jun
Outline plans to address areas of inequality and/or under representation | bar: Q1 Apr to Q1 Jun
Implementing talent conversations
Adapting existing appraisal framework to explore performance, potential, aspirations and readiness | bar: Q2 Jul to Q2 Sep
Utilise outcomes from review and career conversations to inform development/workforce plans | bar: Q2 Jul to Q2 Sep
Establishing review boards/panels at Board level
Socialise principles of Talent Review board and succession planning with Executive Team | bar: Q3 Oct to Q3 Dec
Brief Executive Team on Talent Board | bar: Q3 Oct to Q3 Dec
Brief Sub-Board on Talent Review Principles | bar: Q3 Oct to Q3 Dec
Facilitate at Executive level to create Board level succession plan | bar: Q3 Oct to Q3 Dec
Feedback to individuals | bar: Q3 Oct to Q3 Dec
Collate information to information succession, workforce plans and inform regional interventions | bar: Q3 Oct to Q3 Dec
Succession Planning
Succession planning framework identified | bar: Q4 Jan to Q4 Mar
If appropriate, hard to fill/critical roles identified to prioritise SP activity | bar: Q4 Jan to Q4 Mar
Succession planning takes place as part of talent review activity | bar: Q4 Jan to Q4 Mar
Risk and actions recorded | bar: Q4 Jan to Q4 Mar
Review takes place | bar: Q4 Jan to Q4 Mar
Evaluation
Establish baselines against which the impact of TM can be measured | bar: Q1 Apr to Q1 Jun
Establish range of methods to evaluate and gather feedback on impact of TM | bar: Q1 Apr to Q1 Jun
Carry out qualitative and quantitative evaluation | bar: Q4 Jan to Q4 Mar
Review progress against TM related KPIS | bar: Q4 Jan to Q4 Mar
Use result to refresh approach | bar: Q4 Jan to Q4 Mar

## EXAMPLE B
EXAMPLE TM Implementation Plan | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | STATUS | ACTION OWNER | Comments on progress/additional resources needed/update on risks/actions:
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
YEAR 1 20XX - 20XX
Ensure appropriate foundations for effective talent management are in place
Agree strategy and approach with all stakeholders
Adapting existing appraisal processes to ensure that all conversations include assessments of performance, potential, aspirations, readiness, development and support
Consolidate existing development opportunities and career pathways for staff at all levels to ensure there are clear offers in place and expectations can be managed effectively
Brief staff who will be receiving conversations and training line managers who will be holding conversations in their roles and responsibilities
Identify critical roles and implementing talent review and succession processes to ensure effective management of talent pipelines
Establish talent review approaches for the Board/Executive team in order to meet the requirement of having a robust succession plan in place at level
Further engagement with national and regional programmes of work including Regional Talent Board, High Potential, Training and Graduate Schemes to ensure the organisation is appropriately represented and that opportunities maximised
Evaluate impact of approach to ensure goals and desired outcomes have been achieved. Updating the strategy as necessary to reflect new priorities
Updating strategy as necessary to reflect new priorities
YEAR 2 20XX - 20XX
Implement refinements to approach based on evaluation of Year 1 activities in readiness for wider roll out across the organisation
Continue roll out across clinical and corporate services.
Further development of capability of line managers who have responsibilities in participating in talent management activities and ccontinuation of roll out of briefings to staff who will be receiving conversations to aid their preparation
Identification of critical roles beyond the senior leadership team in order that the organisation can take a planned approach to building succession pipelines
Establish Divisional talent reviews to ensure robust succession plans are in place more broadly across the organisation
Establish further opportunities for development and/or support where appropriate to facilitate smooth career transitions for staff at all levels
Ensure that approaches support the effective identification of individuals’ suitability for participation in local and regional programmes such as the Regional Talent Board, High Potential Scheme and/or other national development offers
Tighten up reporting frameworks in relation to talent activities and implement frameworks to ensure stakeholders receive appropriate and timely information about progress with the organisation’s approach, identified risks and mitigating actions
Evaluating the impact of approach to ensure goals and desired outcomes are achieved Update the strategy as necessary to reflect new priorities.
YEAR 3 20XX - 20XX
Implement refinements to our approach based on evaluation of our Year 2 activities in readiness for wider roll out across the organisation
Ensure the approach is fully rolled out across all clinical and corporate services.
Focus on the development of flexible opportunities across and outside of the organisation to ensure the effective mobilisation/deployment of talent
Engage relevant stakeholders the development/full refresh of the talent strategy to reflect new priorities and ensure it remains responsive to the needs of individuals and the organisation, and it is aligned to local system requirements.
Evaluating the impact of our approach to ensure our goals have been achieved and it is achieving the desired outcomes.

## BLANK
TALENT MANAGEMENT IMPLEMENTATION PLAN | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | STATUS | ACTION OWNER | Comments on progress/additional resources needed/update on risks/actions:
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
KEY DELIVERABLE/YEAR 1
Action 1
Action 2
Action 3
Action 4
Action 5
KEY DELIVERABLE/YEAR 2
Action 6
Action 7
Action 8
Action 9
Action 10
KEY DELIVERABLE/YEAR 3
Action 11
Action 12
Action 13
Action 14
Action 15
KEY DELIVERABLE/YEAR 4
Action 16
Action 17
Action 18
Action 19
Action 20